## Sheet1
Project Summary Costs
|  | Labor Total (Approximate) |  | 16322.75
|  | Furniture and Equipment |  | 58500
|  | Project Total (Approx) |  | 74822.75
Labor Costs
Hourly Rate
| Linda Mulherin |  |  | 48
| Nick Serafin |  |  | 45
| Ajit Singh |  |  | 52
| Victoria Dunn |  |  | 50
| Robert Adams |  |  | 57
| Shraddha Sawant |  |  | 75
|  |  | Average | 54.5
[5 empty] | Time(hrs) | Hourly Rate | Approx. Cost
Initiate Project
Develop Project Charter |  |  |  |  | 10 | 54.5 | 545
Project Kickoff Meeting
Conference Room Meeting |  |  |  |  | 2 | 54.5 | 109
Tour Warehouse Facility |  |  |  |  | 1.5 | 54.5 | 81.75
Review and Approval of Project Charter |  |  |  |  | 2 | 54.5 | 109
Develop Project Plan |  |  |  |  | 10 | 54.5 | 545
Plan Project
Gather and Document the requirements
Determine and document the design for placement of furniture |  |  |  |  | 10 | 54.5 | 545
Determine and document all the hardware requirements and network connectivities |  |  |  |  | 6 | 54.5 | 327
Determine and document all the software requirements |  |  |  |  | 6 | 54.5 | 327
Specify Material
Communicate with the Procurement Department to determine preferred vendor and specify Cubicle Furniture |  |  |  |  | 6 | 54.5 | 327
Communicate with the Procurement Department to determine preferred vendor and specify Laptop |  |  |  |  | 4 | 54.5 | 218
Communicate with the Procurement Department to determine preferred vendor and specify VoIP Handsets |  |  |  |  | 4 | 54.5 | 218
Communicate with the Procurement Department to determine preferred vendor for purchasing Zerox LaserJet multi-functional color network printer-copier |  |  |  |  | 3 | 54.5 | 163.5
Coordinate with the Procurement Department to understand the vendor preference for the purchase of cat 6e cable and ME3400 aggregation switch |  |  |  |  | 3 | 54.5 | 163.5
Coordinate with the Procurement Department to determine the vendor preference for the purchase of Cisco Aironet wireless access points |  |  |  |  | 3 | 54.5 | 163.5
Procurement
Build a order list and obtain cost quotation for each item on the list |  |  |  |  | 12 | 54.5 | 654
Place Order | [5 empty] | 54.5
Order Cubicle Furniture |  |  |  |  | 3 | 54.5 | 163.5
Order Laptops |  |  |  |  | 3 | 54.5 | 163.5
Order VoIP Handsets |  |  |  |  | 2 | 54.5 | 109
Order Zerox LaserJet multi-functional color network printer-copier |  |  |  |  | 2 | 54.5 | 109
Order cat 6e cable and ME3400 aggregation switch |  |  |  |  | 3 | 54.5 | 163.5
Order Cisco Aironet wireless access points |  |  |  |  | 2 | 54.5 | 109
Execute Project
Receive and Inspect
R&I Cubicle Furniture |  |  |  |  | 10 | 54.5 | 545
R&I Laptops |  |  |  |  | 10 | 54.5 | 545
R&I VoIP Handsets |  |  |  |  | 8 | 54.5 | 436
R&I Zerox LaserJet multi-functional color network printer-copier |  |  |  |  | 4 | 54.5 | 218
R&I Cat 6e cable and ME3400 aggregation switch |  |  |  |  | 4 | 54.5 | 218
R&I Cisco Aironet wireless access points |  |  |  |  | 4 | 54.5 | 218
Installation and Configuration
Install Cubicle Furniture
Assemble the furniture |  |  |  |  | 20 | 54.5 | 1090
Place the assembled furniture in assigned office space |  |  |  |  | 8 | 54.5 | 436
Install Laptops
Install all the required hardware |  |  |  |  | 10 | 54.5 | 545
Establish a connectivity to the existing cloud storage solution for all laptops |  |  |  |  | 5 | 54.5 | 272.5
Load the laptops with the Windows 10 Enterprise operating system, Microsoft Office Professional 2019 Suite, Microsoft Security Essentials and Adobe Creative Cloud |  |  |  |  | 9 | 54.5 | 490.5
Install VoIP Handsets
Install all the required hardware |  |  |  |  | 6 | 54.5 | 327
Extend the connectivity of the existing VoIP PBX (phone system) to the newly installed handsets |  |  |  |  | 4 | 54.5 | 218
Install and set-up a connection between the Zerox LaserJet printer-copier and the network in the old warehouse area |  |  |  |  | 4 | 54.5 | 218
Install cat 6e cable and ME3400 aggregation switch
Connect cat 6e cable from each of the 10 cubicles to a data closet in the old warehouse |  |  |  |  | 5 | 54.5 | 272.5
Install ME3400 aggregation switch and connect it to the data closet in old warehouse |  |  |  |  | 5 | 54.5 | 272.5
Ensure a connection between ME3400 aggregation switch and Telco Corp.’s main router (Cisco 1002-X) in the main server room using existing multimode fiber |  |  |  |  | 3 | 54.5 | 163.5
Install Cisco Aironet wireless access points
Install and connect each access point to the Cisco ME3400 aggregation switch in the data closet using cat 6e cable |  |  |  |  | 6 | 54.5 | 327
Configure each access point to use WPA2 encryption for Wi-Fi access |  |  |  |  | 5 | 54.5 | 272.5
Testing
Verify Cubicle Furniture Operations and Conditions along with its placement |  |  |  |  | 3 | 54.5 | 163.5
Test the compatibility and working of each laptop |  |  |  |  | 3 | 54.5 | 163.5
Test the working of the entire VoIP handset set-up |  |  |  |  | 3 | 54.5 | 163.5
Test the working of printer-copier and its capability of shared printing from any PCs in the network |  |  |  |  | 2 | 54.5 | 109
Test the access to all company resources and working of Cisco ASA firewall protected WAN connection for Internet and external traffic through the Cat 6e cable and ME3400 aggregation switch setup |  |  |  |  | 3 | 54.5 | 163.5
Test the working of Cisco Aironet wireless access points framework |  |  |  |  | 5 | 54.5 | 272.5
Close Project
Seek Sponsor Approval
Sponsor Inspection |  |  |  |  | 3 | 54.5 | 163.5
Fix Open Items |  |  |  |  | 30 | 54.5 | 1635
Final Inspection |  |  |  |  | 3 | 54.5 | 163.5
Final Documentation and Archiving |  |  |  |  | 8 | 54.5 | 436
Release Project Team Members |  |  |  |  | 9 | 54.5 | 490.5
|  |  |  | Labor Total (Approximate) | 299.5 | 54.5 | 16322.75
Equipment and Furniture Costs |  |  |  |  | Number | Cost (each) | Total
Laptops with s/w suite |  |  |  |  | 10 | 1850 | 18500
VoIP Handsets |  |  |  |  | 10 | 650 | 6500
Cubicle Furnitures |  |  |  |  | 10 | 2215 | 22150
Zerox LaserJet Multi-Functional High-speed Copier/Printer |  |  |  |  | 1 | 5750 | 5750
Cisco Aironet Wireless Access Points |  |  |  |  | 5 | 525 | 2625
Cisco 1002-X Aggregation Switch |  |  |  |  | 1 | 2350 | 2350
Cat 6E Network Cabling |  |  |  |  | 1 | 625 | 625
|  |  |  | Equipment and Furniture Total |  |  | 58500